Notes

UA Coordination Call

2015-10-28 23:00 UTC

V0.1

| Attendance | Ram Mohan, Christian Dawson (45 min), Dusan Stojicevic, Mark Svancarek, Edmon Chung, Dennis Tan, Don Hollander, Michael Palage, Alina Syunkova | Apologies: Brent London, Rich Merdinger. |
| --- | --- | --- |
| Branding | Twitter/Facebook Handles: GetReadyUA Domain Name: Consider alternatives, including multiple names in multiple TLDs | Christian to revise the domain name exercise. |
| Reactive Issues Testing |  | Christian to organize a Reactive Issue Exercise. |
| Logo | - Decided not to pursue trademark. - Decided to pursue registering all UASG work under Creative Commons Licenses | Don to seek advise from ICANN legal |
| White Paper Scoping Document |  | Don and Ram to discuss and report back |
| Linkification | Noted results from Dublin Meeting – Linkification is within scope for Web addresses & email addresses in context |  |
| Generic CIO Guidelines | Mark is working on the fourth edition of his document, but would very much welcome input. |  |
| Confusable Characters |  | Dennis to resume work with an ETA for next UA Coordination Call |
| Report to GAC & ALAC | GAC support well received. UA included in GAC Communique. ALAC provides additional volunteers and outreach. Opportunity to tap into ALAC’s Outreach Working Group |  |
| Dublin Flyer – now IGF Flyer | Waiting for formatting |  |
| IGF | Christian, Mark & Edmon all attending. Christian to co-chair, introduce session. Carolina Aguerrre to write session report. First draft expected 1st week of November |  |
| Outreach | Create some editorial on UA out of Dublin and going into IGF. | - Ram to ask Circle ID for a UASG identify - Christian to prepare initial draft blog - Christian to look at generating some video for IGF. |
| Asana | Decided NOT to spend money on Asana, but to reconsider how we use it – or possibly an alternative tool | Don to get lesson in Asana use from Edmon |
| Introduction to UA – Continued Work | We discussed the most effective way to get work advanced on the CIO’s Guide to UA and other work. We have a trusted potential candidate. We’ll develop a statement of work and circulate that along with the CV of the candidate and see if there are objections from the community of pressing ahead. | - Mark to prepare statement of work. - Mark to confirm with candidate that it’s ok to circulate their details. - Ram to circulate statement of work and candidate details and determine if there are any objections. |
| ICANN55 Constituency Outreach |  | Don to write to AC’s and SO’s seeking time on their agendas for ICANN55. Don to follow-up in February. |
| DC Meeting Logistics | Don noted the possibility of too many participants and seeking a plan B, possibly at Verisign. This raised the issue of travel funding protocols. | Don to develop travel funding protocols for meetings of the UASG Coordination Group. |
| Mailing List | UA-China. This raised discussion of the role and protocols for UASG support of regional, national and local UA initiatives. | Don to draft protocol for UA Mailing list use. With respect to UA-China, it will be targeted at the CDNC communities and will be clear that it does not commit UASG to secretariat or funding support. |
| Thanks | Ram expressed appreciation for those who stepped in while he was unable to attend the ICANN54 meeting. |  |